## Overview
Internal Accessibility Audit Tool — Project Plan
Project Name | A11y Audit Tool (Internal)
Goal | Build an internal Chrome extension + API platform to audit company web apps for WCAG 2.2 AA compliance using axe-core, Pa11y, and Puppeteer/Playwright with support for authenticated flows.
Stack | TypeScript, React (extension UI + dashboard), Node.js (Fastify/NestJS API), PostgreSQL, Redis (BullMQ), Playwright, axe-core, Pa11y, Docker, Kubernetes
Distribution | Chrome enterprise force-install policy (no public web store)
Auth | Company SSO (Okta / Azure AD / Google Workspace) via OAuth2 + JWT
Estimated Duration | 12-14 weeks for v1.0 (MVP at ~6 weeks)
Team Size | 2 senior fullstack + 1 QA + 0.5 DevOps + 0.5 a11y SME
Epic Count | 8
Story Count | 52
Total Estimated Points | ~340
Phasing | Phase 1 (MVP, weeks 1-6): Epics 1-4. Phase 2 (weeks 7-10): Epics 5-6. Phase 3 (weeks 11-14): Epics 7-8.
Priority Legend
P0 | Blocker — must ship in MVP
P1 | High — needed for v1.0
P2 | Medium — v1.1 / nice to have
P3 | Low — backlog

## Epics
Epic ID | Epic Name | Description | Priority | Phase | Story Points | Dependencies | Owner | Acceptance Criteria
EPIC-01 | Foundation & Infrastructure | Set up monorepo, CI/CD pipelines, base API skeleton, database schema, authentication, and deployment infrastructure. | P0 | Phase 1 | 30 | - | Platform Lead | All services deployable to staging via CI. SSO login works end-to-end. Database migrations run. Health endpoints return 200.
EPIC-02 | Scan Engine Core | Build the scanning engine that runs axe-core + Pa11y against URLs and produces normalized, deduplicated results mapped to WCAG 2.2. | P0 | Phase 1 | 55 | EPIC-01 | Backend Lead | Single-page scan returns merged axe + Pa11y results in <30s. WCAG 2.2 mapping covers all AA criteria. Results deduplicated by (rule, selector).
EPIC-03 | Chrome Extension | Build Chrome extension (MV3) that scans the current page, displays results inline, and syncs to API. | P0 | Phase 1 | 50 | EPIC-01, EPIC-02 | Frontend Lead | Extension scans current tab in <10s. Violations highlighted in-page. Results posted to API. Sideload-ready package builds in CI.
EPIC-04 | Authenticated Flow Testing | Enable scanning of pages behind login via session replay, credential injection, or recorded flows. | P0 | Phase 1 | 45 | EPIC-02 | Backend Lead | Tester can record a login flow once; tool replays it on subsequent scans. Supports 3 auth methods (cookie, form, token). Encrypted credential storage.
EPIC-05 | Crawler & Scheduled Scans | Server-side Playwright crawler with depth/scope controls, queued via BullMQ, with cron-based scheduled scans. | P1 | Phase 2 | 40 | EPIC-02, EPIC-04 | Backend Lead | Crawler discovers SPA routes. Configurable depth/exclude patterns. Scheduled jobs run reliably. 500-page site scans in <30 min.
EPIC-06 | Dashboard & Reporting | Internal web dashboard for browsing scan results, trends, ownership, and generating Excel/PDF reports matching the company report template. | P1 | Phase 2 | 50 | EPIC-02, EPIC-05 | Frontend Lead | Dashboard shows trends, per-app scores, violation lists. Excel export matches reference template. PDF export works.
EPIC-07 | CI/CD & Workflow Integrations | GitHub Action / GitLab CI plugin, Jira ticket auto-creation, Slack/Teams notifications. | P1 | Phase 3 | 35 | EPIC-02, EPIC-06 | Platform Lead | PR check fails on new violations. Jira tickets auto-create with correct project/owner. Slack messages include actionable summary.
EPIC-08 | Custom Rules & Manual Review | Custom axe rule framework for design-system-specific checks, manual review workflow, false-positive triage. | P2 | Phase 3 | 35 | EPIC-02, EPIC-06 | A11y SME + Backend | At least 5 design-system-specific custom rules shipped. Triage UI lets reviewers mark issues as confirmed/false-positive/needs-review.

## Stories & Tasks
Ticket ID | Epic | Type | Title | Description / User Story | Acceptance Criteria | Technical Notes | Priority | Points | Dependencies
T-001 | EPIC-01 | Task | Set up monorepo with pnpm workspaces | Create monorepo structure: /apps (api, dashboard, extension), /packages (shared types, axe-mapping, wcag-rules), /infra. | pnpm install runs cleanly. Each app builds in isolation. Shared TS types used across apps without duplication. | Use pnpm workspaces + Turborepo for build caching. ESLint + Prettier configs at root. Strict TS config. | P0 | 3 | -
T-002 | EPIC-01 | Task | Configure CI/CD pipeline (GitHub Actions) | Set up CI to lint, type-check, test, and build all apps on PR. Auto-deploy to staging on main merge. | PR pipeline runs in <5min. Failed tests block merge. Staging deploy auto-triggers on main. Production deploy is manual approval. | Use GitHub Actions matrix builds. Cache pnpm store. Use OIDC for cloud deploys (no long-lived secrets). | P0 | 5 | T-001
T-003 | EPIC-01 | Task | Provision PostgreSQL + Redis in staging/prod | Set up managed PostgreSQL (RDS/CloudSQL) and Redis instances. Configure VPC, backups, monitoring. | DB reachable from API service only (no public access). Daily backups verified. Redis TLS enabled. | Use Terraform for infra-as-code. Enable point-in-time recovery for Postgres. Redis ACLs for queue isolation. | P0 | 5 | -
T-004 | EPIC-01 | Story | API service skeleton with health checks | As a platform engineer, I want a base API service with health endpoints so I can verify deployment. | GET /health returns 200 with version info. GET /health/ready checks DB + Redis connectivity. Structured JSON logging. | Use Fastify (faster than Express, built-in schema validation). Pino for logging. OpenTelemetry for tracing. | P0 | 3 | T-003
T-005 | EPIC-01 | Story | Database schema + migrations | As a backend dev, I need core tables (users, teams, sites, scans, violations) so I can persist scan data. | Migrations apply cleanly. Schema covers users, teams, sites, scans, violations, scheduled_scans tables. Foreign keys + indexes defined. | Use Prisma or Drizzle ORM. All migrations reversible. Seed script for dev environment. | P0 | 5 | T-004
T-006 | EPIC-01 | Story | SSO authentication via company IdP | As an employee, I want to log in with my company SSO so I do not need a separate account. | OAuth2 authorization code flow works with company IdP. JWT issued with user info + team membership. Tokens expire in 8h, refresh works. | Use openid-client. Store refresh tokens encrypted in Redis. Map IdP groups to internal teams via config. | P0 | 8 | T-004, T-005
T-007 | EPIC-01 | Task | API rate limiting + request validation | Add rate limiting per user/IP and JSON schema validation for all endpoints. | Rate limit returns 429 with Retry-After. Invalid request bodies return 400 with field-level errors. Limits configurable per route. | Use @fastify/rate-limit + Fastify schemas (which leverage Ajv). | P1 | 3 | T-004
T-008 | EPIC-01 | Task | Containerize services + Kubernetes manifests | Dockerize all services. Write Helm charts for staging/prod deployment. | Images <500MB. Containers run as non-root. Helm install succeeds in staging. Liveness/readiness probes wired up. | Multi-stage Docker builds. Use distroless base images. Helm chart with values.staging.yaml and values.prod.yaml. | P0 | 5 | T-004
T-009 | EPIC-02 | Story | axe-core integration in scan worker | As the scan engine, I need to run axe-core against a rendered page and capture all violations. | Worker takes a URL, launches Playwright, injects axe-core, runs all WCAG 2.0/2.1/2.2 A+AA rules, returns raw results. | Use Playwright (better than Puppeteer for our needs). Bundle axe-core@4.x. Run with all WCAG tags. | P0 | 5 | T-005, T-008
T-010 | EPIC-02 | Story | Pa11y integration in scan worker | As the scan engine, I need to run Pa11y (HTMLCS runner) for cross-validation with axe. | Worker also runs Pa11y on the same page and returns raw HTMLCS findings. | Reuse the Playwright browser instance across both engines. Pa11y standard: WCAG2AA. | P0 | 5 | T-009
T-011 | EPIC-02 | Story | WCAG 2.2 mapping table | As a report consumer, I need every finding mapped to the exact WCAG 2.2 success criterion. | Lookup table covers all WCAG 2.2 A+AA criteria. Maps axe rule IDs and HTMLCS codes to SC numbers + level + plain description. | Static JSON in /packages/wcag-rules. Include 2.2 new criteria: 2.4.11, 2.4.12, 2.5.7, 2.5.8, 3.2.6, 3.3.7, 3.3.8. | P0 | 8 | T-009, T-010
T-012 | EPIC-02 | Story | Result deduplication & merging | As a report reader, I do not want to see the same issue reported twice by axe and Pa11y. | Findings dedup by (WCAG_SC + DOM selector). When both engines flag, mark "high confidence". When only one, mark "needs review". | Normalize selectors (handle :nth-child variations). Output a single ScanResult shape. | P0 | 8 | T-011
T-013 | EPIC-02 | Story | Custom rule: WCAG 2.2 SC 2.5.8 (Target Size) | As an a11y tester, I want target-size violations flagged automatically because axe coverage is incomplete. | Custom rule measures bounding box of all interactive elements. Flags <24x24 unless spacing exception applies. | Write as axe custom rule. Account for inline link exception per WCAG 2.2 spec. | P1 | 5 | T-009
T-014 | EPIC-02 | Story | Custom rule: WCAG 2.2 SC 2.4.11 (Focus Not Obscured) | As a keyboard user, I need focused elements to remain visible — automate detection. | Custom rule tabs through page, captures focused element bbox, checks if obscured by sticky/fixed elements. | Use Playwright keyboard.press('Tab') in a loop. Compare focused element bbox vs sticky element bboxes. | P1 | 8 | T-013
T-015 | EPIC-02 | Story | Multi-viewport scan (mobile/tablet/desktop) | As a tester, I want scans run at multiple viewports to catch responsive a11y issues. | Single scan job runs at 375x667, 768x1024, 1440x900 by default. Configurable. Results tagged with viewport. | Reuse Playwright context, change viewport between runs. Adds ~3x runtime. | P1 | 5 | T-009
T-016 | EPIC-02 | Task | BullMQ job queue for scan execution | Wire scan workers to a BullMQ queue so scans run async and scale horizontally. | POST /scans creates a job. Worker pool processes jobs. Failed jobs retry 3x with exponential backoff. Status visible via API. | Separate queue for single-page vs crawl jobs. Use Redis Streams for durability. | P0 | 5 | T-009, T-003
T-017 | EPIC-02 | Story | Scan result storage + retrieval API | As a frontend, I need REST endpoints to submit/retrieve scan results. | POST /v1/scans creates scan. GET /v1/scans/:id returns results. GET /v1/scans?site_id=... lists. All endpoints respect team ACL. | Use cursor pagination. Index on (team_id, created_at). | P0 | 5 | T-005, T-016
T-018 | EPIC-03 | Task | Extension scaffold (MV3 + Vite + React) | Set up Chrome extension with TypeScript, React, Vite build, manifest v3. | pnpm build produces a sideload-able zip. HMR works in dev. Manifest validates. | Use crxjs/vite-plugin. Service worker entry point. React for popup + devtools panel. | P0 | 5 | T-001
T-019 | EPIC-03 | Story | Popup UI: Scan current tab | As a developer, I want to click the extension icon and scan the current page with one click. | Click extension → popup opens → "Scan this page" button → progress indicator → results list grouped by severity. | Use chrome.scripting.executeScript to inject. Show toast on completion. | P0 | 8 | T-018, T-009
T-020 | EPIC-03 | Story | Content script: axe-core execution | As the extension, I need to run axe-core against the live DOM of any page. | Content script injects bundled axe-core, runs against document, returns violations to background worker. | Bundle axe-core (no remote code per MV3 rules). Handle shadow DOM via axe options. | P0 | 5 | T-018
T-021 | EPIC-03 | Story | In-page violation highlighting | As a developer, I want to click a violation and have it highlighted on the page. | Clicking violation in popup highlights element with red outline + scrolls into view. Tooltip shows WCAG SC + fix suggestion. | Use overlay div with absolute positioning over target element bbox. Cleanup on popup close. | P1 | 5 | T-020
T-022 | EPIC-03 | Story | DevTools panel for detailed inspection | As a developer, I want a DevTools panel like Lighthouse for power-user inspection. | New "A11y" tab in DevTools. Lists violations with element selector, code snippet, WCAG link, fix code example. | devtools_page in manifest. Use chrome.devtools.inspectedWindow.eval to inspect DOM. | P1 | 8 | T-020
T-023 | EPIC-03 | Story | Sync results to API | As a team, we want scans run by anyone to be visible to the team via the dashboard. | After scan, results auto-sync to API with user JWT. User can opt out per-scan ("private scan"). | Use chrome.storage.local for offline queue if API unreachable. Sync on next launch. | P0 | 5 | T-019, T-017
T-024 | EPIC-03 | Story | SSO login flow in extension | As an employee, I want to authenticate the extension using my company SSO. | First launch shows "Sign in with company SSO" button. Opens auth window. Token stored securely. | Use chrome.identity.launchWebAuthFlow. Token in chrome.storage.session (cleared on browser close). | P0 | 5 | T-006, T-018
T-025 | EPIC-03 | Task | Enterprise sideload package + update server | Package extension as .crx with auto-update manifest hosted on internal server. | Force-install policy installs extension on test laptop. Update manifest XML serves new versions. Updates within 24h. | Sign with company-owned key. Host updates.xml on internal CDN. Document GPO/MDM setup. | P0 | 5 | T-018
T-026 | EPIC-04 | Story | Auth method: cookie/session injection | As a tester, I want to paste a session cookie to scan pages requiring login. | UI accepts cookie name/value/domain. Crawler sets cookie before scan. Cookie encrypted at rest. | AES-256-GCM encryption with KMS-managed key. Auto-purge cookies after 30 days. | P0 | 5 | T-016
T-027 | EPIC-04 | Story | Auth method: form-based credential injection | As a tester, I want to provide test username/password + form selectors so the tool logs in itself. | Config: login URL, username selector, password selector, submit selector, success indicator (URL/element). Crawler logs in then scans. | Validate selectors before saving. Encrypt creds at rest. Mask in logs. Limit to designated test accounts only. | P0 | 8 | T-026
T-028 | EPIC-04 | Story | Auth method: recorded flow replay | As a tester, I want to record a complex login (e.g., MFA, multi-step) once and have the tool replay it. | Browser extension records clicks/inputs. Saves as Playwright script. Crawler replays before each scan. | Use Playwright codegen format. Encrypt recorded scripts. Allow placeholder for OTP via API callback. | P1 | 13 | T-027
T-029 | EPIC-04 | Task | Encrypted credential vault | Centralized service for storing/retrieving test creds with audit logging. | All cred reads/writes audited. Access requires service-to-service token. Periodic rotation supported. | Use HashiCorp Vault or AWS Secrets Manager. Never log decrypted values. | P0 | 8 | T-006
T-030 | EPIC-04 | Story | Session refresh on long crawls | As a crawler, I need to detect when a session expires mid-crawl and re-authenticate. | Crawler detects redirect-to-login. Re-runs auth flow. Resumes crawl from current page. | Detect login-page heuristics (URL pattern, page content). Max 3 re-auth attempts per crawl. | P1 | 5 | T-027
T-031 | EPIC-05 | Story | Same-origin URL discovery | As a tester, I want to scan all pages of a site by entering one URL. | Crawler follows same-origin links up to configurable depth. Respects robots.txt (toggleable). | Use BFS traversal. Dedupe URLs. Configurable max-pages. | P1 | 8 | T-016
T-032 | EPIC-05 | Story | SPA route discovery | As a tester scanning a SPA, I want client-side routes discovered, not just <a href>. | Crawler hooks history.pushState/replaceState. Follows in-app navigation events. | Inject script that monkey-patches history API. Capture all route changes. | P1 | 8 | T-031
T-033 | EPIC-05 | Story | Scope controls (include/exclude patterns) | As a tester, I want to exclude /admin or /logout URLs from a crawl. | Per-site config supports include/exclude regex patterns. Crawler skips excluded URLs. | Validate regex on save. Show preview of what would match. | P1 | 3 | T-031
T-034 | EPIC-05 | Story | Scheduled scans (cron) | As a team lead, I want nightly scans of our app so we catch regressions automatically. | UI to schedule scans (cron expression). Scheduler triggers crawl. Results compared to last run for diff. | Use BullMQ repeatable jobs. Support timezone. Fail alert if scan misses 2 consecutive runs. | P1 | 8 | T-031, T-016
T-035 | EPIC-05 | Story | New vs existing violation diff | As a developer, I only want to see violations introduced since last scan. | Each scan compared to previous baseline. Violations classified: new / persisting / fixed. | Match by (rule_id + selector + page_url). Surface "new" prominently in dashboard. | P1 | 8 | T-034
T-036 | EPIC-05 | Task | Crawler resource limits + concurrency | Prevent runaway crawls from exhausting resources. | Per-job memory + time limits. Max 5 concurrent pages per crawl. Total worker concurrency configurable. | Use Playwright BrowserContext per page. Kill workers exceeding limits. | P0 | 5 | T-031
T-037 | EPIC-06 | Task | Dashboard scaffold (Next.js + Tailwind) | Set up internal dashboard app with auth, layout, navigation. | Next.js app deploys to internal URL. SSO login works. Basic nav: Sites / Scans / Reports / Settings. | Next.js 14+ App Router. Tailwind + shadcn/ui. SSR for auth pages. | P0 | 5 | T-006
T-038 | EPIC-06 | Story | Sites registry UI | As a team lead, I want to register the apps my team owns so scans are organized. | Add/edit/delete sites. Each site has: name, base URL, owner team, Slack channel, Jira project. | Form with validation. RBAC: only team members can edit team sites. | P1 | 5 | T-037
T-039 | EPIC-06 | Story | Scan results detail page | As a developer, I want to view all violations from a scan with full context. | Page shows: scan summary, violations grouped by severity/WCAG SC, filter/sort, screenshot per violation, recommendation. | Server components for fast initial load. Client-side filter/sort. | P0 | 8 | T-037, T-017
T-040 | EPIC-06 | Story | Trends dashboard per site | As a team lead, I want to see if our compliance is improving over time. | Line chart of total violations / new violations / fixed over last 30/90 days. Per-severity breakdown. | Use Recharts. Aggregate query in Postgres with materialized views. | P1 | 8 | T-039
T-041 | EPIC-06 | Story | Excel report export (matches company template) | As a stakeholder, I want to download an Excel report in our company format with Status / Automated / Manual sheets. | Export button generates .xlsx exactly matching reference template (Status, automated testing, Manual Audit Failures sheets with same columns). | Use ExcelJS or openpyxl. Template-driven generation. Column widths and styles match reference. | P1 | 8 | T-039
T-042 | EPIC-06 | Story | PDF report export | As a stakeholder, I want a PDF version for distribution to non-technical readers. | PDF includes executive summary, violation list with screenshots, WCAG mapping, recommendations. | Use Playwright print-to-PDF or react-pdf. Branded header/footer. | P1 | 5 | T-041
T-043 | EPIC-06 | Story | Manual audit findings entry UI | As a manual tester, I want to log NVDA/VoiceOver findings that automation cannot detect. | Form to add manual findings: page, defect, severity, expected/actual, WCAG SC, screenshot upload. | Findings tagged source=manual. Appear in same scan results alongside automated. | P1 | 8 | T-039
T-044 | EPIC-07 | Story | GitHub Action for PR a11y check | As a developer, I want my PR to fail if it introduces new a11y violations. | Action accepts: app-id, baseline-branch, fail-on-severity. Posts PR comment with diff. Sets check status. | Action runs scan against PR preview URL. Compares to baseline. JS-based action. | P1 | 8 | T-035, T-017
T-045 | EPIC-07 | Story | Jira ticket auto-creation | As a team lead, I want new violations to become Jira tickets automatically in the right project. | Per-site config: Jira project, default assignee, severity threshold. New violations create tickets with full context. | Use Jira Cloud REST API. Idempotency key prevents duplicates. Re-open ticket if violation reappears. | P1 | 8 | T-038
T-046 | EPIC-07 | Story | Slack/Teams notifications | As a team, we want a Slack message when a scheduled scan finds new high-severity issues. | Per-site config: Slack channel webhook. Message includes: site name, new issue count, top 3 issues, dashboard link. | Slack incoming webhooks + Teams adaptive cards. Respect quiet hours config. | P1 | 5 | T-034, T-038
T-047 | EPIC-07 | Task | CLI tool for ad-hoc scans | CLI that hits the API for scans from local dev or any CI system. | pnpm install -g @company/a11y-cli. Commands: scan <url>, login, status. Outputs JSON or human-readable. | Use commander.js. Reads token from keychain on macOS, libsecret on Linux. | P2 | 5 | T-017
T-048 | EPIC-08 | Story | Custom rule framework | As an a11y SME, I need a way to add design-system-specific rules without forking axe. | Plugin folder. Each rule: id, WCAG SC, selector, evaluate function, message. Loaded at scan worker startup. | Define rules using axe.configure. Tested via Jest. Documented in README. | P2 | 8 | T-009
T-049 | EPIC-08 | Story | Design-system custom rules (5 rules) | As a developer, I want our internal design-system component patterns checked. | At least 5 rules covering company button/modal/form patterns. Each rule has test fixtures. | Examples: <CompanyButton> must have icon-only labelling, <Modal> must trap focus, <Form> must announce errors. | P2 | 13 | T-048
T-050 | EPIC-08 | Story | Triage workflow (confirm / false positive / needs review) | As a reviewer, I want to mark findings as confirmed or false-positive so noise reduces over time. | Each violation has triage state. False-positive findings hidden from default views. Audit log of triage actions. | Soft-delete pattern. Triage decisions feed back to confidence scoring. | P2 | 8 | T-039
T-051 | EPIC-08 | Story | Manual review assignment | As a team lead, I want to assign manual review of "needs review" findings to a specific person. | Assign button on violation. Assignee gets notification. Dashboard view for "my queue". | Reuse Slack notification infra. | P2 | 5 | T-050
T-052 | EPIC-08 | Story | Educational tooltips with fix examples | As a developer, I want to learn how to fix issues without leaving the dashboard. | Each WCAG SC has tooltip: plain explanation, before/after code example, link to WCAG docs. | Static content in /packages/wcag-rules. Reviewed by a11y SME. | P2 | 8 | T-011

## Test Plan
Test ID | Linked Ticket | Test Type | Test Title | Preconditions | Test Steps | Expected Result | Priority
TC-001 | T-011 | Unit | WCAG mapping returns correct SC for axe rule | WCAG mapping table loaded | 1. Call mapAxeRule("color-contrast") 2. Inspect result | Returns { sc: "1.4.3", level: "AA", version: "2.0" } | P0
TC-002 | T-012 | Unit | Deduplication merges identical findings from axe + Pa11y | Mock axe and Pa11y results with one identical violation | 1. Pass both result sets to merger 2. Inspect output | Single violation with confidence="high" and sources=["axe","pa11y"] | P0
TC-003 | T-013 | Unit | Target size rule flags 20x20 button | Test fixture HTML with <button style="width:20px;height:20px"> | 1. Run target-size custom rule 2. Inspect violations | One violation flagged with WCAG 2.5.8 | P1
TC-004 | T-013 | Unit | Target size rule respects inline link exception | Test fixture with <a> inline in paragraph text, smaller than 24px | 1. Run target-size custom rule 2. Inspect violations | No violation (inline link exception applies per WCAG 2.2) | P1
TC-005 | T-014 | Unit | Focus obscured rule detects sticky-header overlap | Test fixture with sticky header and form below | 1. Tab through form fields 2. Capture focused bbox vs sticky bbox | Violation when focused field intersects sticky header | P1
TC-006 | T-009,T-010 | Integration | Single-page scan executes axe + Pa11y end-to-end | Test page deployed at http://test-fixture.local with known violations | 1. POST /v1/scans with URL 2. Wait for completion 3. GET results | Scan completes <30s. Returns ≥3 violations matching fixture's known issues. Both axe and Pa11y findings present. | P0
TC-007 | T-016 | Integration | Scan job retries on transient failure | Mock browser launch to fail once then succeed | 1. Submit scan 2. Observe retry behavior | First attempt fails. Second attempt succeeds. Final scan record marked completed. | P0
TC-008 | T-017 | Integration | Scan results respect team ACL | User A in team-1, User B in team-2. Site owned by team-1. | 1. User A creates scan 2. User B attempts to GET scan 3. Inspect response | User B receives 403 | P0
TC-009 | T-027 | Integration | Form-based auth login + scan | Test app with /login form. Test creds in vault. | 1. Configure form auth for site 2. Submit scan for /dashboard 3. Inspect results | Scan succeeds. Results from /dashboard (not redirected to login). | P0
TC-010 | T-031 | Integration | Crawler discovers all linked pages within depth | Test site with index → 3 sub-pages → 1 deeper page | 1. Start crawl with depth=2 2. Inspect crawled URLs | 4 pages crawled (index + 3 sub-pages). Depth-3 page not crawled. | P1
TC-011 | T-035 | Integration | New violation diff calculated correctly | Run scan A (5 violations), modify fixture (fix 2, add 1), run scan B | 1. Compare scan B vs scan A 2. Inspect classifications | 3 persisting, 2 fixed, 1 new | P1
TC-012 | T-019 | E2E | Extension scans current page from popup | Extension installed, user logged in | 1. Navigate to test fixture page 2. Click extension icon 3. Click "Scan this page" 4. Wait | Results panel shows violations within 10s. List sortable by severity. | P0
TC-013 | T-021 | E2E | Clicking violation highlights element on page | Scan completed, results visible in popup | 1. Click first violation in list 2. Observe page | Element scrolled into view. Red outline visible. Tooltip shown. | P1
TC-014 | T-024 | E2E | Extension SSO login flow | Fresh extension install | 1. Click extension icon 2. Click "Sign in" 3. Complete SSO 4. Return to extension | Token stored. Extension shows logged-in state. Subsequent scans authenticated. | P0
TC-015 | T-041 | E2E | Excel export matches reference template | Completed scan with mixed automated + manual findings | 1. Open scan in dashboard 2. Click Export Excel 3. Open downloaded file 4. Compare to reference | File has Status, automated testing, Manual Audit Failures sheets. Columns match reference exactly. Data populates correctly. | P1
TC-016 | T-044 | E2E | GitHub Action fails PR with new high-severity violation | Test repo with action configured. PR introduces a missing-alt-text issue. | 1. Open PR 2. Wait for action 3. Inspect check status + comment | Action fails. PR comment lists new violation. Check status: failed. | P1
TC-017 | T-026,T-027 | Security | Stored credentials encrypted at rest | Cred saved via UI | 1. Inspect database row directly 2. Verify password field | Password field is ciphertext, not plaintext. Decryption requires KMS. | P0
TC-018 | T-027 | Security | Credentials never appear in logs | Form auth scan in progress | 1. Run scan 2. Search all log streams for password value | Password value not found in any log line. | P0
TC-019 | T-006 | Security | Expired JWT rejected | JWT issued, then expired | 1. Make API call with expired token 2. Inspect response | 401 returned with token-expired error code. | P0
TC-020 | T-007 | Security | Rate limiting prevents abuse | API endpoint with 100 req/min limit | 1. Send 150 requests in 60s 2. Observe responses | First 100 succeed. Subsequent return 429 with Retry-After. | P1
TC-021 | T-009 | Performance | Single-page scan completes in <30s for typical page | Test fixture page (~500 DOM nodes) | 1. Run 100 scans 2. Measure p95 latency | p95 < 30s. p99 < 60s. | P1
TC-022 | T-031 | Performance | 500-page crawl completes in <30 min | Site fixture with 500 pages | 1. Start crawl 2. Measure total time | Total time < 30 min. No worker crashes. Memory stable. | P1
TC-023 | T-016 | Performance | Queue handles 100 concurrent scan submissions | Workers scaled to 10 | 1. Submit 100 scans simultaneously 2. Monitor queue + completion | All 100 scans complete within SLA. Queue depth drains. No errors. | P1
TC-024 | T-037 | Accessibility | Dashboard passes its own a11y audit | Dashboard deployed | 1. Run our scan engine against the dashboard itself 2. Inspect results | Zero high or critical violations. Dashboard meets WCAG 2.2 AA. | P0
TC-025 | T-019 | Accessibility | Extension popup keyboard-navigable | Extension popup open | 1. Press Tab repeatedly 2. Verify focus visible on each control 3. Activate scan via Enter | All controls reachable. Focus visible. Scan triggerable without mouse. | P0

## Definition of Done
Category | Criterion | Required For
Code | Code reviewed by at least one other engineer | All tickets
Code | TypeScript strict mode passes (no any without justification) | All tickets
Code | ESLint + Prettier pass with zero warnings | All tickets
Tests | Unit tests cover all new logic, ≥80% coverage on new code | Stories + Tasks
Tests | Integration tests for any new API endpoint or worker | Stories
Tests | E2E test for any user-facing flow | Stories with UI
Security | No secrets committed (verified by gitleaks in CI) | All tickets
Security | Dependencies scanned (Snyk/Dependabot), no high CVEs | All tickets
Security | Auth/authz tests for new endpoints | Backend stories
Documentation | README updated if architecture or setup changes | All tickets
Documentation | API endpoint documented in OpenAPI spec | API stories
Documentation | User-facing changes documented in internal Confluence | User-facing stories
Accessibility | Tool UI itself passes WCAG 2.2 AA (eat our own dog food) | UI stories
Observability | Logs added at INFO/ERROR level for new flows | Stories
Observability | Metrics emitted for new operations (counter / histogram) | Stories
Observability | Alerts configured for new failure modes | Critical path stories
Deployment | Feature flag for risky changes | High-risk stories
Deployment | Migration is reversible / safe to roll back | DB schema changes
Deployment | Deployed to staging and verified before prod merge | All stories
Acceptance | Demo to PM/SME and acceptance criteria signed off | All stories

## Sprint Plan
Sprint | Weeks | Theme | Tickets | Goal / Demo
Sprint 1 | Weeks 1-2 | Foundation | T-001, T-002, T-003, T-004, T-005, T-006, T-008 | Infra deployed. SSO works. API skeleton with health checks live in staging.
Sprint 2 | Weeks 3-4 | Scan Engine MVP | T-007, T-009, T-010, T-011, T-012, T-016, T-017 | Scan a single URL via API; get merged axe + Pa11y results mapped to WCAG 2.2.
Sprint 3 | Weeks 5-6 | Extension MVP + Auth Flows | T-018, T-019, T-020, T-023, T-024, T-025, T-026, T-027, T-029 | MVP DEMO: Sideload extension; SSO login; scan public page + scan a logged-in page via cookie injection. Results in API.
Sprint 4 | Weeks 7-8 | Crawler + Scheduled Scans | T-013, T-014, T-021, T-022, T-028, T-031, T-032, T-033, T-036 | Multi-page crawl works on a SPA. WCAG 2.2 custom rules (target size, focus obscured) live.
Sprint 5 | Weeks 9-10 | Dashboard + Reports | T-015, T-030, T-034, T-035, T-037, T-038, T-039, T-040, T-041, T-043 | V1 DEMO: Dashboard shows trends per app. Excel export matches reference template. Manual findings entry works.
Sprint 6 | Weeks 11-12 | Workflow Integrations | T-022, T-042, T-044, T-045, T-046 | GitHub Action fails PRs on new violations. Jira tickets auto-create. Slack notifications on scheduled scan failures.
Sprint 7 | Weeks 13-14 | Custom Rules + Polish | T-047, T-048, T-049, T-050, T-051, T-052 | V1.0 RELEASE: Design-system custom rules. Triage workflow. Educational tooltips. Roll out to first 3 pilot teams.

## Risks
Risk ID | Risk | Likelihood | Impact | Mitigation | Owner
R-01 | Stored test credentials leak via logs/database | Low | Critical | Encrypted vault. Mask in logs (redaction middleware). Periodic credential rotation. Restrict access via service auth. | Security + Backend Lead
R-02 | Sites with CAPTCHA on login cannot be auto-scanned | High | Medium | Provide manual cookie-import as fallback. Document limitation. Allow tester to bypass CAPTCHA on test accounts. | A11y SME
R-03 | Scan results have high false-positive rate, eroding trust | Medium | High | Confidence scoring. Triage workflow. Tune custom rules with SME. Regular FP audits. | A11y SME + Backend Lead
R-04 | MV3 service worker idle behavior breaks long scans | Medium | Medium | Use chrome.alarms to keep alive. Persist scan state to chrome.storage. Resume on wake. | Frontend Lead
R-05 | Extension permission scope blocks Chrome Web Store approval | N/A | N/A | Internal-only via enterprise force-install. Not a concern for this project. | Platform Lead
R-06 | Crawler runs out of resources on large SPAs | Medium | Medium | Per-job memory + time limits. Page concurrency caps. Auto-kill runaway workers. Prefer breadth-first with dedup. | Backend Lead
R-07 | Tool becomes shelfware — built but not used | Medium | High | Pilot with 3 teams from sprint 5. CI/CD integration ships in sprint 6 (forces adoption). Quarterly usage reviews. | Product / Eng Manager
R-08 | Automation overstates coverage; missed manual issues hurt users | Medium | High | Reports clearly state "automated coverage ≈ 50-60% of WCAG". Manual audit workflow first-class. SME-led review of high-risk apps. | A11y SME
R-09 | WCAG 2.2 spec evolves or new guidance lands | Low | Medium | Version mapping table. Quarterly review with a11y SME. Subscribe to W3C updates. | A11y SME
R-10 | Cross-origin iframes cannot be scanned | High | Low | Document limitation. Encourage same-origin testing of embedded content separately. | Backend Lead